## Front End
Test # | Name | Description | Expected Outcome | 2015-06-27 | 2015-06-29 | 2015-07-01 | 2015-07-03 | 2015-07-05 | 2015-07-06
1 | Home Page | Review Layout and Format | Layout and format match design | Fail | Partial | Partial | Partial | Success | Success
2 | Home Page Links | Links are functioning | * FDA Terms of Use - Open new tab/window and display OpenFDA Terms of Use * OpenFDA Initiative - Open new tab/window and display OpenFDA Site * Drug Search - Redirects to Drug Search Page * Our Solution - Redirects to Out Solution Page * www.intellectsolutions.com - Open new tabl/window to Intellect Solution Page * Privacy Policy - Redirects to Privacy Page * Legal Notice - Redirects to Legal Notice Page | Fail | Partial | Partial | Success | Success | Success
3 | Our Solution | Video is Available | Check to make sure the video is available and runs when the play button is clicked | Fail | Fail | Fail | Fail | Success | Success
4 | Feedback | Feedback Google Form | Check to make sure the form displays and accepts user input | Fail | Fail | Partial | Partial | Success | Success
5 | About Us | Review Layout and Format | Layout and format match design | Fail | Partial | Partial | Partial | Success | Success
6 | Drug Search | Review Query Interface | * Data displays showing drugs having default adverse effect * Selecting Medicine from Drop Down causes graph and label information to update and Demographic Filter to display * Changing Demographic filter results in corresponding change to graphic | Fail | Partial | Partial | Success | Success | Success

## Back End
Test # | Name | Description | Expected Outcome | 2015-06-27 | 2015-06-29 | 2015-07-01 | 2015-07-03 | 2015-07-05 | 2015-07-06
1 | Test List Brand Name OTC Drugs | Submit the following get request to port 8000 on server: /openfda/listBrandNameOTCDrugs | JSON Response with a list of terms and counts | Success | Success | Success | Success | Success | Success
2 | Test List Brand Name Prescription Drugs | Submit the following get request to port 8000 on server: /openfda/listBrandNamePrescriptionDrugs | JSON Response with a list of terms and counts | Success | Success | Success | Success | Success | Success
3 | Test List Generic OTC Drugs | Submit the following get request to port 8000 on server: /openfda/listGenericOTCDrugs | JSON Response with a list of terms and counts | Success | Success | Success | Success | Success | Success
4 | Test List Generic Prescription Durgs | Submit the following get request to port 8000 on server: /openfda/listGenericPrescriptionDrugs | JSON Response with a list of terms and counts | Success | Success | Success | Success | Success | Success
5 | Test Clear Cache Feature | Verify cache is cleared and next list requests repopulates the cache | JSON Response indicating the cache is cleared; subsequent queries submitted for tests 1-4 function as expected | Fail | Success | Success | Success | Success | Success
6 | Test Query Type 1 - List Drugs with identified adverse reaction filter | Submit a Query Type 1 Request: Submit the following JSON object as a post request to /openfda/query URL on server port 8000: {"QueryParameters":{"queryType":1,"drugType":1,"drugSource":1,"drugName":"BYETTA","filterIndex":4}} | JSON Response with Meta Data and Results with terms and counts | Fail | Fail | Success | Success | Success | Success
7 | Test Query Type 2 - List Adverse Reaction for selected drug and demographic | Submit a Query Type 2 Request: Submit the following JSON object as a post request to /openfda/query URL on server port 8000: {"QueryParameters":{"queryType":2,"drugType":1,"drugSource":1,"drugName":"BYETTA","filterIndex":4}} | JSON Response with Meta Data and Results with terms and counts | Fail | Fail | Fail | Success | Success | Success
8 | Test Query Type 3 - List Drug Labels for Selected Drug | Submit a Query Type 3 Request: Submit the following JSON object as a post request to /openfda/query URL on server port 8000: {"QueryParameters":{"queryType":3,"drugType":1,"drugSource":1,"drugName":"BYETTA","filterIndex":4}} | JSON Response with Meta Data and Results with detailed label information for selected drug/medicine. | Fail | Fail | Fail | Fail | Success | Success